## FINAL Stacks 3 4 5
SCOTGOLD RESOURCES LTD - CONONISH GOLD PROSPECT | [7 empty] | Phase A Bond | Phase B Bond |  |  |  | 2018 Bond Max Exposure RPI to Feb 2018 | 2022 Proposed Adjustment | Notes 2022 - refer to Bond Commentary
RESTORATION COSTINGS | [5 empty] | RPI 2012-2017 |  | 1.153 |  |  |  | RPI Feb 2012 - Feb 2018 | 1.164 | RPI Feb 2018 - Nov 2022
carried forward with RPI uplift
reduction proposed
increased provision
[8 empty] | Pre-deposition | Max Exposure |  |  | 2018 RPI Adusted | Max Exposure | 1.28
Item | Description | Unit | 2017 Quantity | Rate £ | 2012 SLR Rate | 2017 Rate | 2012 SLR Amount £ | 2017 Amount | 2017 Amount | Assumptions (RPI Feb 2012-Oct 2017 *1.153)
1 | Equipment on-costs | Sum |  |  |  |  | 2800 | 3228.4 | 3228.4 | RPI |  |  | 3259.2 | 4171.776
2 | Removal of Site Infrastructure
2.1 | Removal of processing plant and buildings | Sum |  |  |  |  | 31500 | 36319.5 | 36319.5 | RPI |  |  | 36666 | 46932.48 | office, welfare, and lab are all on hire, potential reduction identified - SCL proposes this be retained as contingency
2.2 | Break out foundations and disposal off site | m3 | 540 | 31.5 | 31.5 | 36.3195 |  | 19612.53 | 19612.53 | RPI rate | 225mm (overestimate, some not as deep) | 36.666 | 19799.64 | 25343.5392 | the intention is to break out concrete to allow drainage, but to leave in situ - SCL proposes this provision be retained as contingency
2.3 | Removal of base of oil/fuel storage area, to licensed facility | Sum |  |  |  |  | 1050 | 1210.65 | 1210.65 | RPI |  |  | 1222.2 | 1564.416
2.3.1 | removal of bulk fuel tank | [12 empty] | - | hired, no removal cost
2.3.2 | clean out interceptors | [12 empty] | 4000 | based on current contractor rate
2.3.3 | clean out sewage treatment plant | [12 empty] | 1800 | based on current contractor rate
2.4 | Removal of security fencing | Sum |  |  |  |  | 2100 | 2421.3 | 2421.3 | RPI |  |  | 2444.4 |  | removed as no security fencing required/installed
2.5 | Removal of water circulation infrastructure (pipe) | m | 1880 | 31.5 | 31.5 |  |  | 2500 | 2500 |  | 1880m pipes (worst case as could be buried in situ) |  | 2500 | 3200 | buried pipes retained in situ (provision for plugging) but also no recirc installed and reduced crossing pipe length used - SCL proposes this be retained as contingency
2.5.1 | Regrading open drains | m3 | 9730 |  | 0.42 | 0.48 |  | 4670.4 | 4670.4 | RPI rate | 9,730m3 material | 0.48888 | 4756.8024 |  | seepage channels, retained around stacks during restoration phase and then should be left to continue to vegetate.
2.5.2 | Break out concrete berms and disposal off site | m2 | 48 | 1.9 | 2.5 | 36.3195 |  | 1743.336 | 1743.336 | as per 2.2 | inlet berms concrete (worst case removal offsite) | 36.666 | 1759.968 | 2252.759
2.6 | Removal of powerlines | Sum |  |  |  |  | 1000 | 1153 | 1153 | RPI |  |  | 1164 | 1489.92
2.7 | Removal of AEA bridge structure off site | Sum |  |  |  |  | 5000 | 5765 | 5765 | RPI |  |  | 5820 | 7449.6
2.7.1 | removal of Forestry burn 'bridge' off site | Sum | [11 empty] | 1500 | new provision, based on labour (2no.) x 8hrs, crane/hiab and trailer
2.8 | Track scarifying | Sum |  |  |  |  | 400 | 461.2 | 461.2 | RPI |  |  | 465.6 | 595.968 | possible double counting at item 3.5.2 - SCL proposes this be retained as contingency
3.1 | Processing Plant Area
3.1.1 | Rooting of plant area | m2 | 5000 |  | 0.2 | 0.2306 |  | 1153 | 1153 | RPI rate |  | 0.2328 | 1164 |  | unecessary as concrete broken up and whole area to be covered with bund material, no compaction
3.1.2 | Lift turves from plant area bund (30% turf recovery) | m2 | 1800 | 1.5 | 2.5 | 2.8825 |  | 5188.5 | 5188.5 | RPI rate | 30% of 6,000m2 bund area | 2.91 | 5238 | 6704.64
3.1.3 | Transport, store and manage stripped turves | m2 | 1800 | 1.2 | 2.5 | 2.8825 |  | 5188.5 | 5188.5 | RPI rate |  | 2.91 | 5238 | 6704.64
3.1.4 | Lift and store mulch/soil | m3 | 1680 | 1.9 | 1.9 | 2.1907 |  | 3680.376 | 3680.376 | RPI rate | 70% of 6,000m2 bund area, 0.4m depth | 2.2116 | 3715.488 | 4755.8246
3.1.5 | Regrade glacial till from screening mound and back edge of plant area | m3 | 19602 | 0.42 | 0.42 | 0.48426 |  | 9492.4645 | 9492.4645 | RPI rate | 50% bund provides 0.3-0.5m cover on plant and bund area | 0.48888 | 9583.0258 | 12266.273 | total bund volume acknowledged as altered but provision for restoration volume remains appropriate
3.1.6 | Rooting of contractors compound | m2 | 1020 | 0.2 | 0.2 | 0.2306 |  | 235.212 | 235.212 | RPI rate |  | 0.2328 | 237.456 | 303.9437
3.1.7 | Lift and spread mulch/soil | m3 | 1680 | 1.9 | 1.9 | 2.1907 |  | 3680.376 | 3680.376 | RPI rate | cf. 3.1.4 | 2.2116 | 3715.488 | 4755.8246
3.1.8 | Replace turves following works to regrade glacial till incl pegging | m2 | 1800 | 4.1 | 7.5 | 8.6475 |  | 15565.5 | 15565.5 | RPI rate | cf. 3.1.3 | 8.73 | 15714 | 20113.92 | no requirement for pegging of turf (demonstrated by experience to date), SCL believes this cost to be excessive - SCL proposes this be retained as contingency
3.2.A | TSF Area (pre-tailings placement Phase A Bond) | [9 empty] | 1:1 prepared, 1:2 stripped - worst case (Stack 1=6,665m2)
3.2.A.1 | Stack 1:1 rock removed to mine | m3 | 6843 |  | 8 | 9.224 |  | 63119.832 |  | RPI rate | assumed basal drain rock layer is removed to mine
3.2.A.2 | Stack 1:1 Lift and spread soil/mulch (70%) | m3 | 1034.16 | 1.9 | 1.9 | 2.1907 |  | 2265.5343 |  | RPI rate | worst case, assumed in separate storage
3.2.A.3 | Stack 1:1 re-placement of turf (30%) | m2 | 1000.8 | 4.1 | 7.5 | 8.6475 |  | 8654.418 |  | RPI rate | worst case, assumed in separate storage
3.4..A.4i | Stack 1:2 regrade |  | 4000 |  | 0.42 | 0.48 |  | 1920 |  | RPI rate | assumed 1:2 stripped 4 months ahead of rock placement
3.2.A.4 | Stack 1:2 spread mulch | m3 | 1034.16 |  | 1.9 | 2.19 |  | 2264.8104 |  | RPI rate | worst case, assumed in separate storage
3.2.A.5 | Stack 1:2 re-placement of turf (30%) | m2 | 1000.8 | 4.1 | 7.5 | 8.6475 |  | 8654.418 |  | RPI rate | worst case, assumed in separate storage
3.2.A.6 | Application of geojute to stabilise peaty soil | m2 | 3336 | 5 | 5 | 5.765 |  | 19232.04 |  | RPI rate | worst case 50% 1:1 and 1:2
3.2.B | TSF Area (maximum extent - worst case Phase B Bond) | [13 empty] | Stacks 3, 4 and 5 as worst case previously agreed, could be reduced as experience and proposed schedule shows a 2 stack overlap likely to continue, and not 3 - SCL proposes this be retained as contingency
3.2.B.1 | Stack 3:2 lift and spread soil/mulch | m3 | 2282.22 |  | 1.9 | 2.1907 |  |  | 4999.6594 | RPI rate | assumed 3:2 has tailings but no restoration | 2.2116 | 5047.3578 | 6460.6179
3.2.B.2 | Stack 3:2 place turf | m2 | 2208.6 |  | 7.5 | 8.65 |  |  | 19104.39 | RPI rate | assumed 3:2 has tailings but no restoration | 8.73 | 19281.078 | 24679.7798
3.2.B.3 | Stack 4 remove rock to u/g | m3 | 4000 |  | 8 | 9.224 |  |  | 36896 | RPI rate | assumed 4 is part prepared e.g. 4 months advance for placement (worst case, assumed basal drain rock layer is removed to mine | 9.312 | 37248 | 47677.44
3.2.B.4 | Stack 4 replace soil/mulch | m3 | 2732.65 |  | 1.9 | 2.1907 |  |  | 5986.4164 | RPI rate | assumed 4 is prepared 4 months ahead for placement | 2.2116 | 6043.5287 | 7735.7168
3.2.B.5 | Stack 4 replace turf | m2 | 2644.5 |  | 7.5 | 8.65 |  |  | 22874.925 | RPI rate | assumed 4 is prepared 4 months ahead for placement | 8.73 | 23086.485 | 29550.7008
3.2.B.6 | Stack 5:1 regrade | m3 | 4000 |  | 0.42 | 0.48426 |  |  | 1937.04 | RPI rate | assumed 5:1 stripped 4 months ahead of rock placement | 0.48888 | 1955.52 | 2503.0656
3.2.B.7 | Stack 5:1 replace soil/mulch | m3 | 2023.215 |  | 1.9 | 2.1907 |  |  | 4432.2571 | RPI rate | assumed 5:1 is stripped | 2.2116 | 4474.5423 | 5727.4141
3.2.B.8 | Stack 5:1 replace turf | m2 | 1957.95 |  | 7.5 | 8.65 |  |  | 16936.2675 | RPI rate | assumed 5:1 is stripped | 8.73 | 17092.9035 | 21878.9165
3.2.B.9 | Application of geojute to stabilise peaty soil | m2 | 3681 | 5 | 5 | 5.765 |  |  | 21220.965 | RPI rate | worst case 50% of 3:2 (6 and 7 being replaced to natural slopes) | 5.82 | 21423.42 |  | review and remove provision as none has proven necessary to date and no steeper slopes are proposed in later stack areas.
3.3 | Settlement Pond
3.3.1 | settlement pond retained | [9 empty] | remove pipes - see 2.5.1 |  |  | 1500 | actually provision is at 2.5 and 2.5.2 - additional allowance here for removal of valve, costing per removal of bridge at 2.7.1
3.4 | Merge western ponds into single water feature | Sum |  |  |  |  | 2100 | 2421.3 | 2421.3 | RPI |  |  | 2444.4 |  | noted previously as item retained in error, western ponds will no longer be present, previously they were lost to S2 and now to HEA2 (assumed complete/competent by this stage)
3.5 | Storage & circulation areas to be reinstated (inc. reduction of access track)
3.5.1 | Rooting compacted ground | m2 | 15000 | 0.2 | 0.2 | 0.2306 |  | 3459 | 3459 | RPI rate |  | 0.2328 | 3492 | 4469.76
3.6 | HEAs 4, 5 and 6 my require restoration | m2 | 1758 | [8 empty] | 8.73 |  | 19644.5952 | Considering the propsoed schedule of works, HEAs 4, 5 and 6 could be open, so assume turfing works on this entire area. As at 3.1.8 rates include pegging and are likely to be excessive - SCL propose this is retained as a contingency.
4 | Planting
4.1 | Western Process Plant Area
4.1.1 | Chemical analysis and input of plant nutrients | Sum |  |  |  |  | 1000 | 1153 | 1153 | RPI |  |  | 1164 | 1489.92 | unlikely to be required - SCL proposes this be retained as contingency
4.1.2 | Hydroseeding over regraded processing area | m2 | 22500 | 0.21 | 0.5 | 0.5765 |  | 12971.25 | 12971.25 | RPI rate |  | 0.582 | 13095 | 6646.8414 | evidence to date shows this to be unecessary - SCL proposes the provision for brash be retained, but in combination with broadcast seeding.
4.1.3 | Cut and spread brash over regraded processing area | ha | 2.25 | 2000 | 2000 | 2306 |  | 5188.5 | 5188.5 | RPI rate |  | 2328 | 5238 | 6704.64
4.1.4 | Broadcast seeding over compound plant area | m2 | 1020 | 0.2 | 0.2 | 0.2306 |  | 235.212 | 235.212 | RPI rate |  | 0.2328 | 237.456 | 303.9437
4.1.5 | Plug plants at 4 per m2 to 15% of the brash area | m2 | 3375 |  | 4 | 4.612 |  | 15565.5 | 15565.5 | RPI rate |  | 4.656 | 15714 |  | SCL suggests that with seeding and brash cover, plug plants are not necessary
4.2.A | TSF Area (pre-tailings placement Phase A Bond)
4.2.A.1 | Broadcast seeding over regraded stack 1 area | m2 | 6672 | 0.2 | 0.2 | 0.2306 |  | 1538.5632
4.2.A.2 | Cut and spread brash over stack 1 area | ha | 0.6672 | 2000 | 2000 | 2306 |  | 1538.5632
4.2.A.3 | Plug plants at 4 per m2 to 15% stack area | m2 | 500.4 | 4 | 4 | 4.612 |  | 2307.8448 |  | RPI rate | 15% of 1:1
4.2.B | TSF Area (maximum extent - worst case Phase B Bond)
4.2.B.1 | Broadcast seeding over regraded stack areas | m2 | 22703.5 | 0.2 | 0.2 | 0.2306 |  |  | 5235.4271 | RPI rate | worst case 3:2 and all of 4 and 5:1 | 0.2328 | 5285.3748 | 6765.2797 | evidence to date shows this to be unecessary - SCL proposes the provision for brash be retained as a contingency, in combination with broadcast seeding.
4.2.B.2 | Cut and spread brash over stack areas | ha | 2.2704 | 2000 | 2000 | 2306 |  |  | 5235.4271 | RPI rate | worst case 5:2 and all of 6 and 7:1 | 2328 | 5285.3748 | 6765.2797
4.2.B.3 | Plug plants at 4 per m2 to 15% stack area | m2 | 2426.55 | 4 | 4 | 4.612 |  |  | 11191.2486 | RPI rate | 15% of 3:2, 4 | 4.656 | 11298.0168 |  | SCL suggests that with seeding and brash cover, plug plants are not necessary
4.2.B.4 | Tree planting (including labour - 2017 rate) |  | 1750 |  |  | 3.6 |  |  | 6300 | new rate | linking across lower part of site | 3.6 | 6300 | 6635.52 | 310/1750 trees are now planted in this area, reduction in provision in this proportion
4.3 | Settlement Pond Area
4.3.1 | Broadcast seeding over reinstated pond access/operational areas | m2 | 500 | 0.2 | 0.2 | 0.2306 |  | 115.3 | 115.3 | RPI rate | allowance 500m2 | 0.2328 | 116.4 | 148.992
4.3.2 | Cut and spread brash over reinstated pond access/operational area | ha | 0.05 | 2000 | 2000 | 2306 |  | 115.3 | 115.3 | RPI rate |  | 2328 | 116.4 | 148.992
4.3.3 | Plug plants at 4 per m2 to 15% of the brash area | m2 | 75 |  | 4 | 4.612 |  | 345.9 | 345.9 | RPI rate |  | 4.656 | 349.2 | 446.976
4.3.4 | Tree planting (including labour - 2017 rate) |  | 250 |  |  | 3.6 |  | 900 | 900 | new rate | lower part of site, settlement pond/link to existing woodland | 3.6 | 900 |  | tree planting now complete in this area
4.5 | Track restoration
4.5.1 | Hydroseeding | m2 | 3500 | 0.21 | 0.5 | 0.5765 |  | 2017.75 | 2017.75 | RPI rate |  | 0.582 | 2037 | 1033.9531 | SCL proposes this should be broadcast seeding.
5 | Secure Boundaries
5.1 | Sealing of mine | Sum |  | 4200 |  |  | 4200 | 4842.6 | 4842.6 | RPI |  |  | 4888.8 | 6257.664
| Sub Total Restoration Works | [6 empty] | 284095.8804 | 334949.8796 |  |  |  | 338077.5258 | 371081.5326
6 | Survey/management
6.1 | Site survey, preparation of restoration scheme and supervision by appointed contractor | % |  | 0.07 | 0.085 | 8.5% |  | 24148.1498 | 28470.7398 |  | query % basis, rather fix value; subsequently agreed |  | 28736.5897 | 31541.9303
| Total Restoration Works | [6 empty] | 308244.0303 | 363420.6194 |  |  |  | 366814.1155 | 402623.4629
7 | Add for Contingencies |  |  | 0.1 |  | 10% |  | 30824.403 | 36342.0619 |  |  |  | 36681.4116 | 40262.3463
| Total Restoration Works incl. contingencies | [6 empty] | 339068.4333 | 399762.6813 |  |  |  | 403495.5271 | 442885.8091
8 | Add for escalation in prices, assumed at 3.5% p.a. for x years | yrs | 2 | 0.035 |  | 0.035 |  | 23734.7903 | 27983.3877 |  |  |  | 28244.6869 | 31002.0066 | SCL suggests 2 year provision remains sensible
| Total Restoration Works incl. contingencies & escalation | [6 empty] | 362803.2236 | 427746.069 |  |  |  | 431740.214 | 473887.8158
9 | Aftercare
9.1 | Monitor, sampling and analysis of processing area | mths | 6 | 300 | 300 | 345.9 |  | 2075.4 | 2075.4 | RPI rate |  | 349.2 | 2095.2 | 2681.856
9.2 | Soil sampling and analysis and nutrient provision | yrs | 1 | 750 | 750 | 864.75 |  | 864.75 | 864.75 | RPI rate |  | 873 | 873 | 1117.44
9.3.A | Moorland Habitat (heath/mire) Phase A Bond
9.3.A.1 | Inspect moor habitat; cut and spread brash over failed areas Yr 1 | ha | 0.59344 | 2000 | 2000 | 2306 |  | 1368.4726 |  |  | full inspection and 20% 'failed' requiring brash
9.3.A.2 | Plug plants at 4 per m2 |  | 890.16 | 4 | 4 | 4.612 |  | 4105.4179 |  |  | 15% cover for 20% 'failed' restored area
9.3.A.3 | Inspect moor habitat; cut and spread brash over failed areas Yr 2 | ha | 0.29672 | 2000 | 2000 | 2306 |  | 684.2363 |  |  | full inspection and 10% requiring further brash
9.3.A.4 | Inspect moor habitat Yrs 3-10 | yrs | 8 | 500 | 500 | 576.5 |  | 4612 |  |  | annual rate for inspection
9.3.A.5 | Tree planting beating up |  | 250 |  |  | 3.6 |  | 900 |  |  | replace 20% per annum for 5 years
9.3.B | Moorland Habitat (heath/mire) Phase B Bond
9.3.B.1 | Inspect moor habitat; cut and spread brash over failed areas Yr 1 | ha | 0.91407 |  | 2000 | 2306 |  |  | 2107.8454 | RPI rate | full inspection and 20% 'failed' requiring brash | 2328 | 2127.955 | 2723.7823
9.3.B.2 | Plug plants at 4 per m2 |  | 1371.105 |  | 4 | 4.612 |  |  | 6323.5363 | RPI rate | 15% cover for 20% 'failed' restored area | 4.656 | 6383.8649 | 8171.347
9.3.B.3 | Inspect moor habitat; cut and spread brash over failed areas Yr 2 | ha | 0.45703 |  | 2000 | 2306 |  |  | 1053.9227 | RPI rate | full inspection and 10% requiring further brash | 2328 | 1063.9775 | 1361.8912
9.3.B.4 | Inspect moor habitat Yrs 3-10 | yrs | 8 | 500 | 500 | 576.5 |  |  | 4612 | RPI rate | annual rate for inspection | 582 | 4656 | 5959.68
9.3.B.5 | Tree planting beating up | % | 800 |  |  | 3.6 |  |  | 2880 | new rate | replace 800 trees over 5 years | 3.6 | 2880 | 3686.4
9.4 | Geotechnical monitoring visits (Stacks, Phase B only) - see sheet 'GeotechRevised for 2017' | sum | 1 |  |  | 13399.3 |  |  | 13399.3 |  | 6-monthly for 2 years, 4 further visits (every two years) |  | 13399.3 | 17151.104
9.5 | Water sampling - see sheet 'WaterRevised for 2017' | sum | 1 |  |  | 20031.15 |  | 20031.15 | 20031.15 |  |  |  | 20031.15 | 25639.872
9.6 | Stock fence removal | m | 778 |  | 4 | 4.612 |  | 3588.136 | 3588.136 |  | southern mine site boundary | 4.656 | 3622.368 | 4636.631
9.7 | Contract Management | yrs | 10 | 1000 | 1000 | 1153 |  | 11530 | 11530 | RPI rate |  | 1164 | 11640 | 14899.2
| Total Aftercare costs | [6 empty] | 49759.5629 | 68466.0404 |  |  |  | 68772.8153 | 88029.2036
10 | Decommissioning &Aftercare Monitoring Condition 32f
| Ecow Monitoring 0 -5 years | [9 empty] | Includes initial baseline visit
ECoW Monitoring 5 -10 years
| ECoW Monitoring 10 - 20 years | yrs | 10 | [8 empty] | 582 | 5820 | 7449.6
| LCoW Monitoring 0 - 5 years | [9 empty] | Includes initial baseline visit
LCoW Monitoring 5- 10years
LCoW Monitoring 10 - 20 years
| Add for Contingencies |  |  | 0.1 |  | 10% |  | 4975.9563 | 6846.604 |  |  |  | 6877.2815 | 8802.9204
| Total Aftercare incl. contingencies | [6 empty] | 54735.5192 | 75312.6444 |  |  |  | 81470.0969 | 104281.724
11 | Add for escalation in prices, assumed at 3.5% p.a. for x years | yrs | 2 | 0.035 |  | 3.5% |  | 3831.4863 | 5271.8851 |  |  |  | 5702.9068 | 7299.7207 | SCL suggests 2 year provision remains sensible
| Total Aftercare incl. contingencies & escalation | [6 empty] | 58567.0055 | 80584.5295 |  |  |  | 87173.0036 | 111581.4446
| Restoration & Aftercare Total | [6 empty] | 421370.2291 | 508330.5986 |  |  |  | 518913.2176 | 585469.2604
12 | NPA legal fees and administration of the bond
| Calling the bond, legal fees | sum | [9 empty] | 3000 | 3000 | 3840
| Year 1, Restoration, monthly admin checking works vs bond remaining | days | 12 | [8 empty] | 582 | 6984 | 8939.52
| Years 2-5, Aftercare, 6-monthly admin checking works vs bond remaining | days | 8 | [8 empty] | 582 | 4656 | 5959.68
| Years 6-20, Aftercare, reduced admin reflecting minimal works anticipated | days | 7.5 | [8 empty] | 582 | 4365 | 5587.2
| NPA administration | [11 empty] | 19005 | 24326.4
| Restoration & Aftercare Total including NPA Contingency | [6 empty] | 421370.2291 | 508330.5986 |  |  |  | 537918.2176 | 609795.6604

## Stacks 5 6 7
SCOTGOLD RESOURCES LTD - CONONISH GOLD PROSPECT | [7 empty] | Phase A Bond | Phase B Bond
RESTORATION COSTINGS
[8 empty] | Pre-deposition | Max Exposure
Item | Description | Unit | 2017 Quantity | Rate £ | 2012 SLR Rate | 2017 Rate | 2012 SLR Amount £ | 2017 Amount | 2017 Amount | Assumptions (RPI Feb 2012-Oct 2017 *1.153)
1 | Equipment on-costs | Sum |  |  |  |  | 2800 | 3228.4 | 3228.4 | RPI
2 | Removal of Site Infrastructure
2.1 | Removal of processing plant and buildings | Sum |  |  |  |  | 31500 | 36319.5 | 36319.5 | RPI
2.2 | Break out foundations and disposal off site | m3 | 540 | 31.5 | 31.5 | 36.3195 |  | 19612.53 | 19612.53 | 225mm (overestimate, some not as deep)
2.3 | Removal of base of oil/fuel storage area, to licensed facility | Sum |  |  |  |  | 1050 | 1210.65 | 1210.65 | RPI | 2421.3
2.4 | Removal of security fencing | Sum |  |  |  |  | 2100 | 2421.3 | 2421.3 | RPI
2.5 | Removal of water circulation infrastructure (pipe) | m | 1880 | 31.5 | 31.5 | 36.3195 |  | 2500 | 2500 | 1880m pipes (worst case as could be buried in situ)
2.5.1 | Regrading open drains | m3 | 9730 |  |  | 0.48 |  | 4670.4 | 4670.4 | 9,730m3 material
2.5.2 | Break out concrete berms and disposal off site | m2 | 48 | 1.9 | 2.5 | 36.3195 |  | 1743.336 | 1743.336 | inlet berms concrete (worst case removal offsite)
2.6 | Removal of powerlines | Sum |  |  |  |  | 1000 | 1153 | 1153 | RPI
2.7 | Removal of AEA bridge structure off site | Sum |  |  |  |  | 5000 | 5765 | 5765 | RPI
2.8 | Track scarifying | Sum |  |  |  |  | 400 | 461.2 | 461.2 | RPI
3.1 | Processing Plant Area
3.1.1 | Rooting of plant area | m2 | 5000 |  |  | 0.2306 |  | 1153 | 1153
3.1.2 | Lift turves from plant area bund (30% turf recovery) | m2 | 1800 | 1.5 | 2.5 | 2.8825 |  | 5188.5 | 5188.5 | 30% of 6,000m2 bund area
3.1.3 | Transport, store and manage stripped turves | m2 | 1800 | 1.2 | 2.5 | 2.8825 |  | 5188.5 | 5188.5
3.1.4 | Lift and store mulch/soil | m3 | 1680 | 1.9 | 1.9 | 2.1907 |  | 3680.376 | 3680.376 | 70% of 6,000m2 bund area, 0.4m depth
3.1.5 | Regrade glacial till from screening mound and back edge of plant area | m3 | 19602 | 0.42 | 0.42 | 0.48426 |  | 9492.4645 | 9492.4645 | 50% bund provides 0.3-0.5m cover on plant and bund area
3.1.6 | Rooting of contractors compound | m2 | 1020 | 0.2 | 0.2 | 0.2306 |  | 235.212 | 235.212
3.1.7 | Lift and spread mulch/soil | m3 | 1680 | 1.9 | 1.9 | 2.1907 |  | 3680.376 | 3680.376 | cf. 3.1.4
3.1.8 | Replace turves following works to regrade glacial till incl pegging | m2 | 1800 | 4.1 | 7.5 | 8.6475 |  | 15565.5 | 15565.5 | cf. 3.1.3
3.2.A | TSF Area (pre-tailings placement Phase A Bond) | [8 empty] | 1:1 prepared, 1:2 stripped - worst case (Stack 1=6,665m2)
3.2.A.1 | Stack 1:1 rock removed to mine | m3 | 6843 |  | 8 | 9.224 |  | 63119.832 |  | assumed basal drain rock layer is removed to mine
3.2.A.2 | Stack 1:1 Lift and spread soil/mulch (70%) | m3 | 1034.16 | 1.9 | 1.9 | 2.1907 |  | 2265.5343 |  | worst case, assumed in separate storage
3.2.A.3 | Stack 1:1 re-placement of turf (30%) | m2 | 1000.8 | 4.1 | 7.5 | 8.6475 |  | 8654.418 |  | worst case, assumed in separate storage
3.2.A.4i | Stack 1:2 regrade | m3 | 4000 |  |  | 0.48 |  | 1920 |  | assumed 1:2 stripped 4 months ahead of rock placement
3.2.A.4 | Stack 1:2 spread mulch | m3 | 1034.16 |  |  | 2.19 |  | 2264.8104 |  | worst case, assumed in separate storage
3.2.A.5 | Stack 1:2 re-placement of turf (30%) | m2 | 1000.8 | 4.1 | 7.5 | 8.6475 |  | 8654.418 |  | worst case, assumed in separate storage
3.2.A.6 | Application of geojute to stabilise peaty soil | m2 | 3336 | 5 | 5 | 5.765 |  | 19232.04 |  | worst case 50% 1:1 and 1:2
3.2.B | TSF Area (maximum extent - worst case Phase B Bond)
3.2.B.1 | Stack 5:2 lift and spread soil/mulch | m3 | 2023.215 |  |  | 2.1907 |  |  | 4432.2571 | assumed 5:2 has tailings but no restoration
3.2.B.2 | Stack 5:2 place turf | m2 | 1957.95 |  |  | 8.6475 |  |  | 16931.3726 | assumed 5:2 has tailings but no restoration
3.2.B.3 | Stack 6 remove rock to u/g | m3 | 4000 |  |  | 9.224 |  |  | 36896 | assumed 6 is part prepared e.g. 4 months advance for placement (worst case, assumed basal drain rock layer is removed to mine
3.2.B.4 | Stack 6 replace soil/mulch | m3 | 2658.87 |  |  | 2.1907 |  |  | 5824.7865 | assumed 6 is prepared 4 months ahead for placement
3.2.B.5 | Stack 6 replace turf | m2 | 2573.1 |  |  | 8.6475 |  |  | 22250.8823 | assumed 6 is prepared 4 months ahead for placement
3.2.B.6 | Stack 7:1 regrade | m3 | 4000 |  |  | 0.48426 |  |  | 1937.04 | assumed 7:1 stripped 4 months ahead of rock placement (half stack, worst case is 7)
3.2.B.7 | Stack 7:1 replace soil/mulch | m3 | 2402.19 |  |  | 2.1907 |  |  | 5262.4776 | assumed 7:1 is stripped
3.2.B.8 | Stack 7:1 replace turf | m2 | 2324.7 |  |  | 8.6475 |  |  | 20102.8433 | assumed 7:1 is stripped
3.2.B.9 | Application of geojute to stabilise peaty soil | m2 | 3263.25 | 5 | 5 | 5.765 |  |  | 18812.6363 | worst case 50% of 5:2 (6 and 7 being replaced to natural slopes)
3.3 | Settlement Pond
3.3.1 | settlement pond retained | [8 empty] | remove pipes - see 2.5.1
3.4 | Merge western ponds into single water feature | Sum |  |  |  |  | 2100 | 2421.3 | 2421.3
3.5 | Storage & circulation areas to be reinstated (inc. reduction of access track)
3.5.2 | Rooting compacted ground | m2 | 15000 | 0.2 | 0.2 | 0.2306 |  | 3459 | 3459
4 | Planting
4.1 | Western Process Plant Area
4.1.1 | Chemical analysis and input of plant nutrients | Sum |  |  |  |  | 1000 | 1153 | 1153
4.1.2 | Hydroseeding over regraded processing area | m2 | 22500 | 0.21 | 0.5 | 0.5765 |  | 12971.25 | 12971.25
4.1.3 | Cut and spread brash over regraded processing area | ha | 2.25 | 2000 | 2000 | 2306 |  | 5188.5 | 5188.5
4.1.4 | Broadcast seeding over compound plant area | m2 | 1020 | 0.2 | 0.2 | 0.2306 |  | 235.212 | 235.212
4.1.5 | Plug plants at 4 per m2 to 15% of the brash area | m2 | 3375 |  | 4 | 4.612 |  | 15565.5 | 15565.5
4.2.A | TSF Area (pre-tailings placement Phase A Bond)
4.2.A.1 | Broadcast seeding over regraded stack 1 area | m2 | 6672 | 0.2 | 0.2 | 0.2306 |  | 1538.5632 |  | worst case whole of 1
4.2.A.2 | Cut and spread brash over stack 1 area | ha | 0.6672 | 2000 | 2000 | 2306 |  | 1538.5632
4.2.A.3 | Plug plants at 4 per m2 to 15% stack 1:1 area | m2 | 500.4 | 4 | 4 | 4.612 |  | 2307.8448 |  | 15% of 1:1
4.2.B | TSF Area (maximum extent - worst case Phase B Bond)
4.2.B.1 | Broadcast seeding over regraded stack areas | m2 | 22852.5 | 0.2 | 0.2 | 0.2306 |  |  | 5269.7865 | worst case 5:2 and all of 6 and 7:1
4.2.B.2 | Cut and spread brash over stack areas | ha | 2.2853 | 2000 | 2000 | 2306 |  |  | 5269.7865 | worst case 5:2 and all of 6 and 7:1
4.2.B.3 | Plug plants at 4 per m2 to 15% stack area | m2 | 2265.525 | 4 | 4 | 4.612 |  |  | 10448.6013 | 15% of 5:2, 6
4.2.B.4 | Tree planting (including labour - 2017 rate) |  | 750 |  |  | 3.6 |  |  | 2700 | linking across lower part of site
4.3 | Settlement Pond Area
4.3.1 | Broadcast seeding over reinstated pond access/operational areas | m2 | 500 | 0.2 | 0.2 | 0.2306 |  | 115.3 | 115.3 | allowance 500m2
4.3.2 | Cut and spread brash over reinstated pond access/operational area | ha | 0.05 | 2000 | 2000 | 2306 |  | 115.3 | 115.3
4.3.3 | Plug plants at 4 per m2 to 15% of the brash area | m2 | 75 |  | 4 | 4.612 |  | 345.9 | 345.9
4.3.4 | Tree planting (including labour - 2017 rate) |  | 250 |  |  | 3.6 |  | 900 | 900 | lower part of site, settlement pond/link to existing woodland
4.5 | Track restoration
4.5.1 | Hydroseeding | m2 | 3500 | 0.21 | 0.5 | 0.5765 |  | 2017.75 | 2017.75
5 | Secure Boundaries
5.1 | Sealing of mine | Sum |  | 4200 | 4200 |  | 4200 | 4842.6 | 4842.6 | RPI
| Sub Total Restoration Works | [6 empty] | 284095.8804 | 328738.3264
6 | Survey/management
6.1 | Site survey, preparation of restoration scheme and supervision by appointed contractor | % |  | 0.07 | 0.085 | 8.5% |  | 24148.1498 | 27942.7577 | query % basis, rather fix value; subsequently agreed
| Total Restoration Works | [6 empty] | 308244.0303 | 356681.0842
7 | Add for Contingencies |  |  | 0.1 |  | 10% |  | 30824.403 | 35668.1084
| Total Restoration Works incl. contingencies | [6 empty] | 339068.4333 | 392349.1926
8 | Add for escalation in prices, assumed at 3.5% p.a. for x years | yrs | 2 | 0.035 |  | 0.035 |  | 23734.7903 | 27464.4435
| Total Restoration Works incl. contingencies & escalation | [6 empty] | 362803.2236 | 419813.6361
9 | Aftercare
9.1 | Monitor, sampling and analysis of processing area | mths | 6 | 300 | 300 | 345.9 |  | 2075.4 | 2075.4
9.2 | Soil sampling and analysis and nutrient provision | yrs | 1 | 750 | 750 | 864.75 |  | 864.75 | 864.75
9.3.A | Moorland Habitat (heath/mire) Phase A Bond
9.3.A.1 | Inspect moor habitat; cut and spread brash over failed areas Yr 1 | ha | 0.59344 | 2000 | 2000 | 2306 |  | 1368.4726 |  | full inspection and 20% 'failed' requiring brash
9.3.A.2 | Plug plants at 4 per m2 |  | 890.16 | 4 | 4 | 4.612 |  | 4105.4179 |  | 15% cover for 20% 'failed' restored area
9.3.A.3 | Inspect moor habitat; cut and spread brash over failed areas Yr 2 | ha | 0.29672 | 2000 | 2000 | 2306 |  | 684.2363 |  | full inspection and 10% requiring further brash
9.3.A.4 | Inspect moor habitat Yrs 3-10 | yrs | 8 | 500 | 500 | 576.5 |  | 4612 |  | annual rate for inspection
9.3.A.5 | Tree planting beating up |  | 250 |  |  | 3.6 |  | 900 |  | replace 20% per annum for 5 years
9.3.B | Moorland Habitat (heath/mire) Phase B Bond
9.3.B.1 | Inspect moor habitat; cut and spread brash over failed areas Yr 1 | ha | 0.91705 |  | 2000 | 2306 |  |  | 2114.7173 | full inspection and 20% 'failed' requiring brash
9.3.B.2 | Plug plants at 4 per m2 |  | 1375.575 |  | 4 | 4.612 |  |  | 6344.1519 | 15% cover for 20% 'failed' restored area
9.3.B.3 | Inspect moor habitat; cut and spread brash over failed areas Yr 2 | ha | 0.45853 |  | 2000 | 2306 |  |  | 1057.3587 | full inspection and 10% requiring further brash
9.3.B.4 | Inspect moor habitat Yrs 3-10 | yrs | 8 | 500 | 500 | 576.5 |  |  | 4612 | annual rate for inspection
9.3.B.5 | Tree planting beating up |  | 750 |  |  | 3.6 |  |  | 2700 | replace 20% per annum for 5 years
9.4 | Geotechnical monitoring visits (Stacks, Phase B only) - see sheet 'GeotechRevised for 2017' | sum | 1 |  |  | 13399.3 |  |  | 13399.3 | 6-monthly for 2 years, 4 further visits (every two years)
9.5 | Water sampling - see sheet 'WaterRevised for 2017' | sum | 1 |  |  | 20031.15 |  | 20031.15 | 20031.15
9.6 | Stock fence removal | m | 778 |  |  | 4.612 |  | 3588.136 | 3588.136 | southern mine site boundary
9.6 | Contract Management | yrs | 10 | 1000 | 1000 | 1153 |  | 11530 | 11530 | RPI
| Total Aftercare costs | [6 empty] | 49759.5629 | 68316.9639
10 | Add for Contingencies |  |  | 0.1 |  | 10% |  | 4975.9563 | 6831.6964
| Total Aftercare incl. contingencies | [6 empty] | 54735.5192 | 75148.6602
11 | Add for escalation in prices, assumed at 3.5% p.a. for x years | yrs | 2 | 0.035 |  | 3.5% |  | 3831.4863 | 5260.4062
| Total Aftercare incl. contingencies & escalation | [6 empty] | 58567.0055 | 80409.0665
| Restoration & Aftercare Total | [6 empty] | 421370.2291 | 500222.7025

## Stacks 7 8 9
SCOTGOLD RESOURCES LTD - CONONISH GOLD PROSPECT | [7 empty] | Phase A Bond | Phase B Bond
RESTORATION COSTINGS
[8 empty] | Pre-deposition | Max Exposure
Item | Description | Unit | 2017 Quantity | Rate £ | 2012 SLR Rate | 2017 Rate | 2012 SLR Amount £ | 2017 Amount | 2017 Amount | Assumptions (RPI Feb 2012-Oct 2017 *1.153)
1 | Equipment on-costs | Sum |  |  |  |  | 2800 | 3228.4 | 3228.4 | RPI
2 | Removal of Site Infrastructure
2.1 | Removal of processing plant and buildings | Sum |  |  |  |  | 31500 | 36319.5 | 36319.5 | RPI
2.2 | Break out foundations and disposal off site | m3 | 540 | 31.5 | 31.5 | 36.3195 |  | 19612.53 | 19612.53 | 225mm (overestimate, some not as deep)
2.3 | Removal of base of oil/fuel storage area, to licensed facility | Sum |  |  |  |  | 1050 | 1210.65 | 1210.65 | RPI | 2421.3
2.4 | Removal of security fencing | Sum |  |  |  |  | 2100 | 2421.3 | 2421.3 | RPI
2.5 | Removal of water circulation infrastructure (pipe) | m | 1880 | 31.5 | 31.5 | 36.3195 |  | 2500 | 2500 | 1880m pipes (worst case as could be buried in situ)
2.5.1 | Regrading open drains | m3 | 9730 |  |  | 0.48 |  | 4670.4 | 4670.4 | 9,730m3 material
2.5.2 | Break out concrete berms and disposal off site | m2 | 48 | 1.9 | 2.5 | 36.3195 |  | 1743.336 | 1743.336 | inlet berms concrete (worst case removal offsite)
2.6 | Removal of powerlines | Sum |  |  |  |  | 1000 | 1153 | 1153 | RPI
2.7 | Removal of AEA bridge structure off site | Sum |  |  |  |  | 5000 | 5765 | 5765 | RPI
2.8 | Track scarifying | Sum |  |  |  |  | 400 | 461.2 | 461.2 | RPI
3.1 | Processing Plant Area
3.1.1 | Rooting of plant area | m2 | 5000 |  |  | 0.2306 |  | 1153 | 1153
3.1.2 | Lift turves from plant area bund (30% turf recovery) | m2 | 1800 | 1.5 | 2.5 | 2.8825 |  | 5188.5 | 5188.5 | 30% of 6,000m2 bund area
3.1.3 | Transport, store and manage stripped turves | m2 | 1800 | 1.2 | 2.5 | 2.8825 |  | 5188.5 | 5188.5
3.1.4 | Lift and store mulch/soil | m3 | 1680 | 1.9 | 1.9 | 2.1907 |  | 3680.376 | 3680.376 | 70% of 6,000m2 bund area, 0.4m depth
3.1.5 | Regrade glacial till from screening mound and back edge of plant area | m3 | 19602 | 0.42 | 0.42 | 0.48426 |  | 9492.4645 | 9492.4645 | 50% bund provides 0.3-0.5m cover on plant and bund area
3.1.6 | Rooting of contractors compound | m2 | 1020 | 0.2 | 0.2 | 0.2306 |  | 235.212 | 235.212
3.1.7 | Lift and spread mulch/soil | m3 | 1680 | 1.9 | 1.9 | 2.1907 |  | 3680.376 | 3680.376 | cf. 3.1.4
3.1.8 | Replace turves following works to regrade glacial till incl pegging | m2 | 1800 | 4.1 | 7.5 | 8.6475 |  | 15565.5 | 15565.5 | cf. 3.1.3
3.2.A | TSF Area (pre-tailings placement Phase A Bond) | [8 empty] | 1:1 prepared, 1:2 stripped - worst case (Stack 1=6,665m2)
3.2.A.1 | Stack 1:1 rock removed to mine | m3 | 6843 |  | 8 | 9.224 |  | 63119.832 |  | assumed basal drain rock layer is removed to mine
3.2.A.2 | Stack 1:1 Lift and spread soil/mulch (70%) | m3 | 1034.16 | 1.9 | 1.9 | 2.1907 |  | 2265.5343 |  | worst case, assumed in separate storage
3.2.A.3 | Stack 1:1 re-placement of turf (30%) | m2 | 1000.8 | 4.1 | 7.5 | 8.6475 |  | 8654.418 |  | worst case, assumed in separate storage
3.2.A.4i | Stack 1:2 regrade | m3 | 4000 |  |  | 0.48 |  | 1920 |  | assumed 1:2 stripped 4 months ahead of rock placement
3.2.A.4 | Stack 1:2 spread mulch | m3 | 1034.16 |  |  | 2.19 |  | 2264.8104 |  | worst case, assumed in separate storage
3.2.A.5 | Stack 1:2 re-placement of turf (30%) | m2 | 1000.8 | 4.1 | 7.5 | 8.6475 |  | 8654.418 |  | worst case, assumed in separate storage
3.2.A.6 | Application of geojute to stabilise peaty soil | m2 | 3336 | 5 | 5 | 5.765 |  | 19232.04 |  | worst case 50% 1:1 and 1:2
3.2.B | TSF Area (maximum extent - worst case Phase B Bond)
3.2.B.1 | Stack 7:2 lift and spread soil/mulch | m3 | 2402.19 |  |  | 2.1907 |  |  | 5262.4776 | assumed 7:2 has tailings but no restoration
3.2.B.2 | Stack 7:2 place turf | m2 | 2324.7 |  |  | 8.6475 |  |  | 20102.8433 | assumed 7:2 has tailings but no restoration
3.2.B.3 | Stack 8 regrade rock | m3 | 4000 |  |  | 9.224 |  |  | 36896 | assumed 8 is part prepared e.g. 4 months advance for placement (worst case, assumed basal drain rock layer is removed to mine
3.2.B.4 | Stack 8 replace soil/mulch | m3 | 1681.75 |  |  | 2.1907 |  |  | 3684.2097 | assumed 8 is prepared 4 months ahead for placement
3.2.B.5 | Stack 8 replace turf | m2 | 1627.5 |  |  | 8.6475 |  |  | 14073.8063 | assumed 8 is prepared 4 months ahead for placement
3.2.B.6 | Stack 9:1 regrade rock | m3 | 4000 |  |  | 0.48426 |  |  | 1937.04 | assumed 9:1 stripped 4 months ahead of rock placement
3.2.B.7 | Stack 9:1 replace soil/mulch | m3 | 981.305 |  |  | 2.1907 |  |  | 2149.7449 | assumed 9:1 is stripped
3.2.B.8 | Stack 9:1 replace turf | m2 | 949.65 |  |  | 8.6475 |  |  | 8212.0984 | assumed 9:1 is stripped
3.2.B.9 | Application of geojute to stabilise peaty soil | m2 | 3874.5 | 5 | 5 | 5.765 |  |  | 22336.4925 | worst case 50% of 7:2 (8 and 9 being replaced to natural slopes)
3.3 | Settlement Pond
3.3.1 | settlement pond retained | [8 empty] | remove pipes - see 2.5.1
3.4 | Merge western ponds into single water feature | Sum |  |  |  |  | 2100 | 2421.3 | 2421.3
3.5 | Storage & circulation areas to be reinstated (inc. reduction of access track)
3.5.2 | Rooting compacted ground | m2 | 15000 | 0.2 | 0.2 | 0.2306 |  | 3459 | 3459
4 | Planting
4.1 | Western Process Plant Area
4.1.1 | Chemical analysis and input of plant nutrients | Sum |  |  |  |  | 1000 | 1153 | 1153
4.1.2 | Hydroseeding over regraded processing area | m2 | 22500 | 0.21 | 0.5 | 0.5765 |  | 12971.25 | 12971.25
4.1.3 | Cut and spread brash over regraded processing area | ha | 2.25 | 2000 | 2000 | 2306 |  | 5188.5 | 5188.5
4.1.4 | Broadcast seeding over compound plant area | m2 | 1020 | 0.2 | 0.2 | 0.2306 |  | 235.212 | 235.212
4.1.5 | Plug plants at 4 per m2 to 15% of the brash area | m2 | 3375 |  | 4 | 4.612 |  | 15565.5 | 15565.5
4.2.A | TSF Area (pre-tailings placement Phase A Bond)
4.2.A.1 | Broadcast seeding over regraded stack 1 area | m2 | 6672 | 0.2 | 0.2 | 0.2306 |  | 1538.5632 |  | worst case whole of 1
4.2.A.2 | Cut and spread brash over stack 1 area | ha | 0.6672 | 2000 | 2000 | 2306 |  | 1538.5632
4.2.A.3 | Plug plants at 4 per m2 to 15% stack area | m2 | 500.4 | 4 | 4 | 4.612 |  | 2307.8448 |  | 15% of 1:1
4.2.B | TSF Area (maximum extent - worst case Phase B Bond)
4.2.B.1 | Broadcast seeding over regraded stack areas | m2 | 16339.5 | 0.2 | 0.2 | 0.2306 |  |  | 3767.8887 | worst case 5:2 and all of 6 and 7:1
4.2.B.2 | Cut and spread brash over stack areas | ha | 1.634 | 2000 | 2000 | 2306 |  |  | 3767.8887 | worst case 5:2 and all of 6 and 7:1
4.2.B.3 | Plug plants at 4 per m2 to 15% stack area | m2 | 1976.1 | 4 | 4 | 4.612 |  |  | 9113.7732 | 15% of 7:2, 8
4.2.B.4 | Tree planting (including labour - 2017 rate) |  | 750 |  |  | 3.6 |  |  | 2700 | linking across lower part of site
4.3 | Settlement Pond Area
4.3.1 | Broadcast seeding over reinstated pond access/operational areas | m2 | 500 | 0.2 | 0.2 | 0.2306 |  | 115.3 | 115.3 | allowance 500m2
4.3.2 | Cut and spread brash over reinstated pond access/operational area | ha | 0.05 | 2000 | 2000 | 2306 |  | 115.3 | 115.3
4.3.3 | Plug plants at 4 per m2 to 15% of the brash area | m2 | 75 |  | 4 | 4.612 |  | 345.9 | 345.9
4.3.4 | Tree planting (including labour - 2017 rate) |  | 250 |  |  | 3.6 |  | 900 | 900 | lower part of site, settlement pond/link to existing woodland
4.5 | Track restoration
4.5.1 | Hydroseeding | m2 | 3500 | 0.21 | 0.5 | 0.5765 |  | 2017.75 | 2017.75
5 | Secure Boundaries
5.1 | Sealing of mine | Sum |  | 4200 | 4200 |  | 4200 | 4842.6 | 4842.6 | RPI
| Sub Total Restoration Works | [6 empty] | 284095.8804 | 306604.1197
6 | Survey/management
6.1 | Site survey, preparation of restoration scheme and supervision by appointed contractor | % |  | 0.07 | 0.085 | 8.5% |  | 24148.1498 | 26061.3502 | query % basis, rather fix value; subsequently agreed
| Total Restoration Works | [6 empty] | 308244.0303 | 332665.4699
7 | Add for Contingencies |  |  | 0.1 |  | 10% |  | 30824.403 | 33266.547
| Total Restoration Works incl. contingencies | [6 empty] | 339068.4333 | 365932.0169
8 | Add for escalation in prices, assumed at 3.5% p.a. for x years | yrs | 2 | 0.035 |  | 0.035 |  | 23734.7903 | 25615.2412
| Total Restoration Works incl. contingencies & escalation | [6 empty] | 362803.2236 | 391547.2581
9 | Aftercare
9.1 | Monitor, sampling and analysis of processing area | mths | 6 | 300 | 300 | 345.9 |  | 2075.4 | 2075.4
9.2 | Soil sampling and analysis and nutrient provision | yrs | 1 | 750 | 750 | 864.75 |  | 864.75 | 864.75
9.3.A | Moorland Habitat (heath/mire) Phase A Bond
9.3.A.1 | Inspect moor habitat; cut and spread brash over failed areas Yr 1 | ha | 0.59344 | 2000 | 2000 | 2306 |  | 1368.4726 |  | full inspection and 20% 'failed' requiring brash
9.3.A.2 | Plug plants at 4 per m2 |  | 890.16 | 4 | 4 | 4.612 |  | 4105.4179 |  | 15% cover for 20% 'failed' restored area
9.3.A.3 | Inspect moor habitat; cut and spread brash over failed areas Yr 2 | ha | 0.29672 | 2000 | 2000 | 2306 |  | 684.2363 |  | full inspection and 10% requiring further brash
9.3.A.4 | Inspect moor habitat Yrs 3-10 | yrs | 8 | 500 | 500 | 576.5 |  | 4612 |  | annual rate for inspection
9.3.A.5 | Tree planting beating up |  | 250 |  |  | 3.6 |  | 900 |  | replace 20% per annum for 5 years
9.3.B | Moorland Habitat (heath/mire) Phase B Bond
9.3.B.1 | Inspect moor habitat; cut and spread brash over failed areas Yr 1 | ha | 0.78679 |  | 2000 | 2306 |  |  | 1814.3377 | full inspection and 20% 'failed' requiring brash
9.3.B.2 | Plug plants at 4 per m2 |  | 1180.185 |  | 4 | 4.612 |  |  | 5443.0132 | 15% cover for 20% 'failed' restored area
9.3.B.3 | Inspect moor habitat; cut and spread brash over failed areas Yr 2 | ha | 0.3934 |  | 2000 | 2306 |  |  | 907.1689 | full inspection and 10% requiring further brash
9.3.B.4 | Inspect moor habitat Yrs 3-10 | yrs | 8 | 500 | 500 | 576.5 |  |  | 4612 | annual rate for inspection
9.3.B.5 | Tree planting beating up |  | 750 |  |  | 3.6 |  |  | 2700 | replace 20% per annum for 5 years
9.4 | Geotechnical monitoring visits (Stacks, Phase B only) - see sheet 'GeotechRevised for 2017' | sum | 1 |  |  | 13399.3 |  |  | 13399.3 | 6-monthly for 2 years, 4 further visits (every two years)
9.5 | Water sampling - see sheet 'WaterRevised for 2017' | sum | 1 |  |  | 20031.15 |  | 20031.15 | 20031.15
9.6 | Stock fence removal | m | 778 |  |  | 4.612 |  | 3588.136 | 3588.136 | southern mine site boundary
9.6 | Contract Management | yrs | 10 | 1000 | 1000 | 1153 |  | 11530 | 11530 | RPI
| Total Aftercare costs | [6 empty] | 49759.5629 | 66965.2558
10 | Add for Contingencies |  |  | 0.1 |  | 10% |  | 4975.9563 | 6696.5256
| Total Aftercare incl. contingencies | [6 empty] | 54735.5192 | 73661.7814
11 | Add for escalation in prices, assumed at 3.5% p.a. for x years | yrs | 2 | 0.035 |  | 3.5% |  | 3831.4863 | 5156.3247
| Total Aftercare incl. contingencies & escalation | [6 empty] | 58567.0055 | 78818.1061
| Restoration & Aftercare Total | [6 empty] | 421370.2291 | 470365.3642

## Summary
Likely 'worst' Stack Scenario | Phase A Bond | Phase B Bond
3-4-5 | 421370.2291 | 508330.5986
5-6-7 | 421370.2291 | 500222.7025
7-8-9 | 421370.2291 | 470365.3642
possible scenarios from mine project schedule (possible worst in bold)
StackNo | GIS Area | LSS Area | 1 | 1,2 | 2,3 | 3,4,5 | 4,5,6 | 5,6,7 | 6,7 | 7,8,9 | 8,9,10 | 9,10 | 10 | rock volume | rock Scenario 2 | half rock | half rock 2
1 | 6665 | 6672 | 6665 | 6665 | [9 empty] | 13686 | 13686 | 6843 | 6843
2 | 11439 | 11418 |  | 11439 | 11439 | [8 empty] | 11896 | 9487 | 5948 | 4743.5
3 | 14724 | 14724 |  |  | 14724 | 14724 | [7 empty] | 12669 | 14891 | 6334.5 | 7445.5
4 | 8815 | 8815 |  |  |  | 8815 | 8815 | [6 empty] | 8514 | 5095 | 4257 | 2547.5
5 | 13053 | 13053 |  |  |  | 13053 | 13053 | 13053 | [5 empty] | 10952 | 13094 | 5476 | 6547
6 | 8577 | 8577 |  |  |  |  | 8577 | 8577 | 8577 |  |  |  |  | 9756 | 7993 | 4878 | 3996.5
7 | 15498 | 15498 | [5 empty] | 15498 | 15498 | 15498 |  |  |  | 15702 | 16612 | 7851 | 8306
8 | 5425 | 5425 | [7 empty] | 5425 | 5425 |  |  | 2991 | 5308 | 1495.5 | 2654
9 | 6331 | 6331 | [7 empty] | 6331 | 6331 | 6331
10 | 5609 | 5608 | [8 empty] | 5609 | 5609 | 5609
area | 96136 | 96121 | 6665 | 18104 | 26163 | 36592 | 30445 | 37128 | 24075 | 27254 | 17365 | 11940 | 5609
Slope Area |  | 98584 | [11 empty] | 86166 | 86166
rock volume |  |  | 4000
bond quantum (2017) |  |  | 421370.2291 |  |  | 508330.5986 |  | 500222.7025 |  | 470365.3642
RPI to 02.2018 | [5 empty] | 518913.2176
subsequent additions | [5 empty] | 537918.2176
N.B. | agreed assumption that 4 months operational area would be prepared for taillings deposition, this equates to around 4,000t bare rock | [9 empty] | we should review these assumptions, only 2 stacks likely to be operational, one under 2nd half restoration, the second having SK prepared, allow half stripped. Although this was accepted by SCL and it's around £30k so not perhaps worth a fuss
agreed assumption that half subsequent stack area (ahead of rock placement) may be stripped.
| 1 | 421370.2291
| 3,4,5 | 508330.5986
| 5,6,7 | 500222.7025
| 7,8,9 | 470365.3642

## GeotechRevised for 2017
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  |  | Visit 1, Yr1 | Visit 2, Yr1 | Visit 3, Yr2 | Visit 4, Yr2 | Visit 5, Yr3 | Visit 6, Yr4 | Visit 7, Yr5 | Visit 8, Yr6 | Visit 9, Yr7 | Visit 10, Yr8 | Visit 11, Yr9 | Visit 12, Yr10
Local Geotechnical Engineer (does not have to be a Geotechnical Specialist, as defined by the Mine Regulations 2014)
| Days for inspection and summary report |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
| Rate |  | 520 | 520 | 520 | 520 | 520 | 520 | 520 | 520 | 520 | 520 | 520 | 520
| Geotech. Total |  | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300
| Expenses, site visit |  | 89.9 | 89.9 | 89.9 | 89.9 | 89.9 | 89.9 | 89.9 | 89.9 | 89.9 | 89.9 | 89.9 | 89.9
| Peer review, hrs |  |  | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Peer review rate |  |  | 95 |  | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95 | 95
| Peer review total |  |  | 380 |  | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380 | 380
| Overall total (per visit) |  | 1389.9 | 1769.9 | 1389.9 | 1769.9 |  | 1769.9 |  | 1769.9 |  | 1769.9 |  | 1770
| 17 year total (17 visits) | 13399.3

## WaterRevised for 2017
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
Local Technician
| Hours per visit |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Rate |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
| Technician fees |  | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
| Expenses |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| Total for technician |  | 252 | 252 | 252 | 252 | 252 | 252 | 252 | 252 | 252 | 252
Water samples
| Frequency per year |  | 4 | 4 | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 1
| No samples |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4
| Cost per sample |  | 86.475 | 86.475 | 86.475 | 86.475 | 86.475 | 86.475 | 86.475 | 86.475 | 86.475 | 86.475
| Total water testing |  | 2075.4 | 2075.4 | 2075.4 | 1037.7 | 518.85 | 518.85 | 518.85 | 345.9 | 345.9 | 345.9
| Transport water samples |  | 230.6 | 230.6 | 230.6 | 115.3 | 57.65 | 57.65 | 57.65 | 57.65 | 57.65 | 57.65
| Results review and letter report (per visit) |  | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325
| Total reporting per year |  | 1300 | 1300 | 1300 | 650 | 325 | 325 | 325 | 325 | 325 | 325
| Total (per year) |  | 3858 | 3858 | 3858 | 2055 | 1153.5 | 1153.5 | 1153.5 | 980.55 | 980.55 | 980.55
| Overall total (10 years) | 20031.15

## ECoW
ECoW |  |  | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
|  |  | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20
Local Technician
Days (including site visit & report | bar: 31 Year 11 to 40 Year 20
| Daily Rate |  | 582 | 582 | 582 | 582 | 582 | 582 | 582 | 582 | 582 | 582
| Total for technician |  | 582 | 582 | 582 | 582 | 582 | 582 | 582 | 582 | 582 | 582
| TOTAL ECoW Monitoring Costs | 5820